## Tabelle1
Checklist
The checklist is compiled of the items of the
- ENSREG "Compilation of recommendations and suggestions" and
- CNS Final Sum. Report 2nd Extraord. Meeting 2012 para. 21 “significant activities and action.."
ENSREG Main Areas of Improvement (European Level Recommendations)
C=CNS
E=ENSREG |  |  |  | Implement Status | Completion scheduled
| Item | Topic
E | 2.1 | general | European guidance on assessment of natural hazards and margins The peer review Board recommends that WENRA, involving the best available expertise from Europe, develop guidance on natural hazards assessments, including earthquake, flooding and extreme weather conditions, as well as corresponding guidance on the assessment of margins beyond the design basis and cliff-edge effects.
E | 2.2 | general | Periodic Safety Review The peer review Board recommends that ENSREG underline the importance of periodic safety review. In particular, ENSREG should highlight the necessity to reevaluate natural hazards and relevant plant provisions as often as appropriate but at least every 10 years.
E | 2.3 | general | Containment integrity Urgent implementation of the recognised measures to protect containment integrity is a finding of the peer review that national regulators should consider.
E | 2.4 | general | Prevention of accidents resulting from natural hazards and limiting their consequences Necessary implementation of measures allowing prevention of accidents and limitation of their consequences in case of extreme natural hazards is a finding of the peer review that national regulators should consider. See also CNS 21.2 "Enhance safety systems to withstand an unexpected natural event"
ENSREG and CNS Considerations (Items to be considered)
Topic 1 - Natural Hazards
| Item | Topic
E | 3.1.1 | 1 | Hazard Frequency The use a return frequency of 10E-4 per annum (0.1g minimum peak ground acceleration for earthquakes) for plant reviews/back-fitting with respect to external hazards safety cases. See also CNS 21.1 "Hazards posed by external events"
C | 21.1 | 1 | Hazards posed by external events re-evaluating the hazards posed by external events, such as earthquakes, floods and extreme weather conditions, for each nuclear power plant site through targeted reassessment of safety.
E | 3.1.2 | 1 | Secondary Effects of Earthquakes The possible secondary effects of seismic events, such as flood or fire arising as a result of the event, in future assessments.
E | 3.1.3 | 1 | Protected Volume Approach The use a protected volume approach to demonstrate flood protection for identified rooms or spaces.
E | 3.1.4 | 1 | Early Warning Notifications The implementation of advanced warning systems for deteriorating wheather, as well as the provision of appropriate procedures to be followed by operators when warnings are made.
E | 3.1.5 | 1 | Seismic Monitoring The installation of seismic monitoring systems with related procedures and training.
E | 3.1.6 | 1 | Qualified Walkdowns The development of standards to address qualified plant walkdowns with regard to earthquake, flooding and extreme weather – to provide a more systematic search for non-conformities and correct them (e.g. appropriate storage of equipment, particularly for temporary and mobile plant and tools used to mitigate beyond design basis (BDB) external events).
E | 3.1.7 | 1 | Flooding Margin Assessments The analysis of incrementally increased flood levels beyond the design basis and identification of potential improvements, as required by the initial ENSREG specification for the stress tests.
E | 3.1.8 | 1 | External Hazard Margins In conjunction with recommendation 1 and 17, the formal assessment of margins for all external hazards including, seismic, flooding and severe weather, and identification of potential improvements.
Topic 2 - Loss of Safety Systems
| Item | Topic
C | 21.2 |  | Enhance safety systems to withstand an unexpected natural event. Upgrading safety systems or installing additional equipment and instrumentation to enhance the ability of each nuclear power plant to withstand an unexpected natural event without access to the electrical power grid for an extended period of time, including for an external event affecting multiple units.
E | 3.2.1 | 2 | Alternate Cooling and Heat Sink The provision of alternative means of cooling including alternate heat sinks. Examples include steam generator (SG) gravity alternative feeding, alternate tanks or wells on the site, air-cooled cooling towers or water sources in the vicinity (reservoir, lakes, etc) as an additional way of enabling core cooling. See also CNS 21.2 "Enhance safety systems to withstand an unexpected natural event"
E | 3.2.2 | 2 | AC Power Supplies The enhancement of the on-site and off-site power supplies. Examples include adding layers of emergency power, adding independent and dedicated backup sources, the enhancement of the grid through agreements with the grid operator on rapid restoration of off-site power, additional and/or reinforced off-site power connections, arrangements for black start of co-located or nearby gas or hydro plants, replacing standard ceramic based items with plastic or other material that are more resistant to a seismic event. Another example is the possible utilisation of generator load shedding and house load operation for increased robustness, however, before introducing such arrangements the risks need to be properly understood. See also CNS 21.2 "Enhance safety systems to withstand an unexpected natural event"
E | 3.2.3 | 2 | DC Power Supplies The enhancement of the DC power supply. Examples include improving the battery discharge time by upgrading the existing battery, changing/diversifying battery type (increasing resistance to common-mode failures), providing spare/replacement batteries, implementing well-prepared loadshedding/staggering strategies, performing real load testing and on-line monitoring of the status of the batteries and preparing dedicated recharging options (e. g. using portable generators).
E | 3.2.4 | 2 | Operational and Preparatory Actions Implementation of operational or preparatory actions with respect to the availability of operational consumables. Examples include, ensuring the supply of consumables such as fuel, lubrication oil, and water and ensuring adequate equipment, procedures, surveillance, drills and arrangements for the resupply from off-site are in place.
E | 3.2.5 | 2 | Instrumentation and Monitoring The enhancement of instrumentation and monitoring. Examples include separate instrumentation and/or power sources to enable monitoring of essential parameters under any circumstances for accident management and the ability to measure specific important parameters based on passive and simple principles.
E | 3.2.6 | 2 | Shutdown Improvements The enhancement of safety in shutdown states and mid-loop operation. Examples of improvements include, reducing or prohibiting mid-loop operation, adding dedicated hardware, procedures and drills, the use of other available water sources (e. g. from hydro-accumulators), requiring the availability of SGs during shutdown operations and the availability of feedwater in all modes.
E | 3.2.7 | 2 | Reactor Coolant Pump Seals The use of temperature-resistant (leak-proof) primary pump seals.
E | 3.2.8 | 2 | Ventilation The enhancement of ventilation capacity during SBO to ensure equipment operability.
E | 3.2.9 | 2 | Main and Emergency Control Rooms The enhancement of the main control room (MCR), the emergency control room (ECR) and emergency control centre (ECC) to ensure continued operability and adequate habitability conditions in the event of a station black-out (SBO) and in the event of the loss of DC (this also applies to Topic 3 recommendations).
E | 3.2.10 | 2 | Spent Fuel Pool The improvement of the robustness of the spent fuel pool (SFP). Examples include reassessment/upgrading SFP structural integrity, installation of qualified and power-independent monitoring, provisions for redundant and diverse sources of additional coolant resistant to external hazards (with procedures and drills), design of pools that prevents drainage, the use of racks made of borated steel to enable cooling with fresh (unborated) water without having to worry about possible recriticality, redundant and independent SFP cooling systems, provision for additional heat exchangers (e. g. submerged in the SFP), an external connection for refilling of the SFP (to reduce the need for an approach linked to high doses in the event of the water falling to a very low level) and the possibility of venting steam in a case of boiling in the SFP. See also CNS 21.3 "Ensure cooling of spent fuel pools"
C | 21.3 | 2 | Ensure cooling of spent fuel pools Installing additional equipment and instrumentation in spent fuel pools to ensure cooling can be maintained or restored in all circumstances, or performing additional technical evaluations to determine if additional equipment and instrumentation are needed.
E | 3.2.11 | 2 | Separation and Independence The enhancement of the functional separation and independence of safety systems. Examples include the elimination of full dependence of important safety functions on auxiliary systems such as service water and the introduction of an alternate source of cooling.
E | 3.2.12 | 2 | Flow Path and Access Availability The verification of assured flow paths and access under SBO conditions. Ensure that the state in which isolation valves fail and remain, when motive and control power is lost, is carefully considered to maximise safety. Enhance and extend the availability of DC power and instrument air (e. g. by installing additional or larger accumulators on the valves). Ensure access to critical equipment in all circumstances, specifically when electrically operated turnstiles are interlocked.
E | 3.2.13 | 2 | Mobile Devices The provision of mobile pumps, power supplies and air compressors with prepared quick connections, procedures, and staff training with drills. Mobile devices are intended to enable the use of existing safety equipment, enable direct feeding of the primary or secondary side, allow extended use of instrumentation and operation of controls, allow effective fire-fighting, and ensure continued emergency lighting. The equipment should be stored in locations that are safe and secure even in the event of general devastation caused by events significantly beyond the design basis (this also applies to Topic 3 recommendations).
E | 3.2.14 | 2 | Bunkered/Hardened Systems The provision for a bunkered or “hardened” system to provide an additional level of protection with trained staff and procedures designed to cope with a wide variety of extreme events including those beyond the design basis (this also applies to Topic 3 recommendations).
E | 3.2.15 | 2 | Multiple Accidents The enhancement of the capability for addressing accidents occurring simultaneously on all plants of the site and consideration of the site as a whole for a multi-units site in the safety assessment. Examples include assuring preparedness and sufficient supplies, adding mobile devices and fire trucks and increasing the number of trained and qualified staff (this also applies to Topic 3 recommendations).
E | 3.2.16 | 2 | Equipment Inspection and Training Programs The establishment of regular programs for inspections to ensure that a variety of additional equipment and mobile devices are properly installed and maintained, particularly for temporary and mobile equipment and tools used for mitigation of BDB external events. Development of relevant staff training programmes for deployment of such devices.
E | 3.2.17 | 2 | Further Studies to Address Uncertainties The performance of further studies in areas were there are uncertainties. Uncertainties may exist in the following areas: 1) The integrity of the SFP and its liner in the event of boiling or external impact. 2) The functionality of control equipment (feedwater control valves and SG relief valves, main steam safety valves, isolation condenser flow path, containment isolation valves as well as depressurisation valves) during the SBO to ensure that cooling using natural circulation would not be interrupted in a SBO. 3) The performance of additional studies to assess operation in the event of widespread damage, for example, the need different equipment (e.g. bulldozers) to clear the route to the most critical locations or equipment. This includes the logistics of the external support and related arrangements (storage of equipment, use of national defence resources, etc.).
Topic 3 - Severe Accident Management
| Item | Topic
E | 3.3.1 | 3 | WENRA Reference Levels The incorporation of the WENRA reference levels related to severe accident management (SAM) into their national legal frameworks, and ensure their implementation in the installations as soon as possible. This would include: · Hydrogen mitigation in the containment - Demonstration of the feasibility and implementation of mitigation measures to prevent massive explosions in case of severe accidents. · Hydrogen monitoring system - Installation of qualified monitoring of the hydrogen concentration in order to avoid dangerous actions when concentrations that allow an explosion exist. · Reliable depressurization of the reactor coolant system - Hardware provisions with sufficient capacity and reliability to allow reactor coolant system depressurization to prevent high-pressure melt ejection and early containment failure, as well as to allow injection of coolant from low pressure sources. · Containment overpressure protection - Containment venting via the filters designed for severe accident conditions. · Molten corium stabilization - Analysis and selection of feasible strategies and implementation of provisions against containment degradation by molten corium.
E | 3.3.2 | 3 | SAM Hardware Provisions Adequate hardware provisions that will survive external hazards (e.g. by means of qualification against extreme external hazards, storage in a safe location) and the severe accident environment (e.g. engineering substantiation and/or qualification against high pressures, temperatures, radiation levels, etc), in place, to perform the selected strategies.
E | 3.3.3 | 3 | Review of SAM Provisions Following Severe External Events The systematic review of SAM provisions focusing on the availability and appropriate operation of plant equipment in the relevant circumstances, taking account of accident initiating events, in particular extreme external hazards and the potential harsh working environment.
E | 3.3.4 | 3 | Enhancement of Severe Accident Management Guidelines (SAMG) In conjunction with the recommendation 4, the enhancement of SAMGs taking into account additional scenarios, including, a significantly damaged infrastructure, including the disruption of plant level, corporate-level and national-level communication, long-duration accidents (several days) and accidents affecting multiple units and nearby industrial facilities at the same time. See also CNS 21.4 "Evaluation of the guidance to manage emergency situations"
C | 21.4 | 3 | Evaluation of the guidance to manage emergency situations Performing or planning an evaluation of the guidance that is to be used by the operator to manage emergency situations resulting from severe accidents caused by extreme natural phenomena at nuclear power plants, including for low power and shutdown states. These documents include emergency operating procedures to prevent core damage, severe accident management guidelines to prevent containment failure, and extensive damage mitigation guidelines to address accidents that result in fires or explosions that affect a large portion of a nuclear power plant.
E | 3.3.5 | 3 | SAMG Validation The validation of the enhanced SAMGs. See also CNS 21.4 "Evaluation of the guidance to manage emergency situations"
E | 3.3.6 | 3 | SAM Exercises Exercises aimed at checking the adequacy of SAM procedures and organisational measures, including extended aspects such as the need for corporate and nation level coordinated arrangements and long-duration events.
E | 3.3.7 | 3 | SAM Training Regular and realistic SAM training exercises aimed at training staff. Training exercises should include the use of equipment and the consideration of multi-unit accidents and long-duration events. The use of the existing NPP simulators is considered as being a useful tool but needs to be enhanced to cover all possible accident scenarios.
E | 3.3.8 | 3 | Extension of SAMGs to All Plant States The extension of existing SAMGs to all plant states (full and low-power, shutdown), including accidents initiated in SFPs.
E | 3.3.9 | 3 | Improved Communications The improvement of communication systems, both internal and external, including transfer of severe accident related plant parameters and radiological data to all emergency and technical support centre and regulatory premises. See also CNS 21.7 "Improving radiation monitoring and communications capabilities"
C | 21.7 | 3 | Improving radiation monitoring and communications capabilities Improving their radiation monitoring and communications capabilities, and enhancing public communications, such as via dedicated public websites.
E | 3.3.10 | 3 | Presence of Hydrogen in Unexpected Places The preparation for the potential for migration of hydrogen, with adequate countermeasures, into spaces beyond where it is produced in the primary containment, as well as hydrogen production in SFPs.
E | 3.3.11 | 3 | Large Volumes of Contaminated Water The conceptual preparations of solutions for post-accident contamination and the treatment of potentially large volumes of contaminated water.
E | 3.3.12 | 3 | Radiation Protection The provision for radiation protection of operators and all other staff involved in the SAM and emergency arrangements. See also CNS 21.7 "Improving radiation monitoring and communications capabilities"
E | 3.3.13 | 3 | On Site Emergency Center The provision of an on-site emergency center protected against severe natural hazards and radioactive releases, allowing operators to stay onsite to manage a severe accident. See also CNS 21.8 "Upgrading regional, off-site and on-site emergency response centres"
C | 21.8 | 3 | Regional, off-site and on-site emergency response centres Upgrading regional, off-site and on-site emergency response centres.
E | 3.3.14 | 3 | Support to Local Operators Rescue teams and adequate equipment to be quickly brought on site in order to provide support to local operators in case of a severe situation. See also CNS 21.8 "Upgrading regional, off-site and on-site emergency response centres"
E | 3.3.15 | 3 | Level 2 Probabilistic Safety Assessments (PSAs) A comprehensive Level 2 PSA as a tool for the identification of plant vulnerabilities, quantification of potential releases, determination of candidate high-level actions and their effects and prioritizing the order of proposed safety improvements. Although PSA is an essential tool for screening and prioritising improvements and for assessing the completeness of SAM implementation, low numerical risk estimates should not be used as the basis for excluding scenarios from consideration of SAM especially if the consequences are very high.
E | 3.3.16 | 3 | Severe Accident Studies The performance of further studies to improve SAMGs. Examples of areas that could be improved with further studies include: · The availability of safety functions required for SAM under different circumstances. · Accident timing, including core melt, reactor pressure vessel (RPV) failure, basemat melt-through, SFP fuel uncovery, etc. · PSA analysis, including all plant states and external events for PSA levels 1 and 2. · Radiological conditions on the site and associated provisions necessary to ensure MCR and ECR habitability as well as the feasibility of AM measures in severe accident conditions, multi-unit accidents, containment venting, etc. · Core cooling modes prior to RPV failure and of re-criticality issues for partly damaged cores, with un-borated water supply. · Phenomena associated with cavity flooding and related steam explosion risks. · Engineered solutions regarding molten corium cooling and prevention of basemat melt-through. · Severe accident simulators appropriate for NPP staff training. See also CNS 21.5 "Probabilistic safety assessments to support severe accident management"
C | 21.5 | 3 | Probabilistic safety assessments to support severe accident management Developing probabilistic safety assessments to identify additional accident management measures or changes in radiation protection measures for workers on the site that might be needed to perform necessary activities in the event of a severe accident.